## Risk assessment
RISK ASSESSMENT (Risk Manager alternative)
Unit/Institute: | University of Coimbra | [5 empty] | Date: |  | 12/12/20203
Responsible line manager (name): | Gonçalo Bastos | [5 empty] | Revised:
Responsible for activities being risk assessed (name): | Gonçalo Bastos
Participants in the risk assement (names): | Gonçalo Bastos
Description of the activity, process, area, etc.:
Sensor Accuracy in Extreme Conditions, Interruption in Data Transmission, Hardware or Software Failure, Overreliance on Emerging Technologies
Activity / process | Unwanted incident | Existing risk reducing measures | Probability (P) | Consequence (C) Evaluate the categories individualley. Health should always be evaluated. |  |  |  | Risk value (P x C) | Risk reducing measures - suggestions Measures reducing the probability of the unwanted incident happening should be prioritized. | Residual risk after measures being implemented (S x K)
|  |  | (1-5) | Health (1-5) | Material values (1-5) | Environment (1-5) | Reputation (1-5)
Sensor Accuracy in Extreme Conditions | Inaccurate data collection. | Constant calibration | 3 | 0 | 5 | 0 | 5 | 15 | Implement robust calibration procedures and use high-quality sensors. Consider environmental testing to ensure performance under different conditions. | 3 (P = 1)
Interrupt Data transmission | Affect real-time data feedback. | None | 1 | 0 | 3 | 0 | 3 | 3 | Design the system with backup communication protocols or data caching mechanisms to handle temporary transmission interruptions. | 3 (P = 1)
Hardware/Software Failure | Could render the device non-functional. | None | 2 | 0 | 5 | 0 | 5 | 10 | Regularly update and test the software for bugs and vulnerabilities. Use reliable hardware components and establish a regular maintenance schedule. | 3 (P = 1)
Overreliance on Emerging Technologies | Challenges in implementation or support. | Scalabilty and simplicity | 3 | 0 | 3 | 0 | 3 | 9 | Keep abreast of technological advancements and have alternative solutions ready. Engage in continuous research and development. | 3 (P = 1)
Risk Identification
Sensor Accuracy in Extreme Conditions
Interruption in Data Transmission
Hardware or Software Failure
Overreliance on Emerging Technologies
Risk Analysis (Likelihood and Impact)
Sensor Accuracy: Medium likelihood, High impact. The sensor may not perform optimally in extreme weather conditions, leading to inaccurate data collection.
Data Transmission: Low likelihood, Medium impact. Interruptions in Bluetooth communication could occur, affecting real-time data feedback.
Hardware/Software Failure: Low likelihood, High impact. Failure in any hardware or software component could render the device non-functional.
Emerging Technologies: Medium likelihood, Medium impact. Relying on emerging technologies could lead to challenges in implementation or support.
Risk Mitigation Strategies
Sensor Accuracy: Implement robust calibration procedures and use high-quality sensors. Consider environmental testing to ensure performance under different conditions.
Data Transmission: Design the system with backup communication protocols or data caching mechanisms to handle temporary transmission interruptions.
Hardware/Software Failure: Regularly update and test the software for bugs and vulnerabilities. Use reliable hardware components and establish a regular maintenance schedule.
Emerging Technologies: Keep abreast of technological advancements and have alternative solutions ready. Engage in continuous research and development.
Monitoring and Review
Establish a routine review process to monitor the identified risks and the effectiveness of the mitigation strategies. Update the risk assessment periodically or when significant changes occur in the project scope or environment.

## Risk matrix explanation
Red | Unacceptable risk. Measures needs to be implemented.
Yellow | Medium risk. Measures needs to be considered.
Green | Acceptable risk. Measures can be considered.
Risk = Probability x Consequence
Consequence
5. Very serious | 5 | 10 | 15 | 20 | 25
4. Serious | 4 | 8 | 12 | 16 | 20
3. Moderate | 3 | 6 | 9 | 12 | 15
2. Small | 2 | 4 | 6 | 8 | 10
1. Very small | 1 | 2 | 3 | 4 | 5
| 1. Very small | 2. Small | 3. Medium | 4. High | 5. Very high
Probability